## Risk log
Project name: Bookstore inventory management system
Project manager: T Ali
ID | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk in this project. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions
1 | Project purpose and need is not well-defined. | Medium | High | High | Project Sponsor | Project specification provided by trainer | Escalate to the trainer to determine the specification required for the project | obtain project specification with clear deliverables
2 | Project design and deliverable definition is incomplete. | Low | High | High | Project Sponsor | Define the scope in detail | ask for a detailed deliverable scope of project to be given
3 | Project schedule is not clearly defined or understood | Low | Medium | Medium | developer | we have a table of milestones to ensure project is delivered on time Go through upcoming tasks in a weekly project progress review. | Revisit the schedule wih the trainer. 'Relaunch' the schedule. | Workshops scheduled.
4 | Estimating and/or scheduling errors | Medium | High | High | developer | Use story points to allocate units of work to tasks, however as a beginner this maynot be the most accurate, so use the milestones laid out as an aide to help meet deadline | Escalate to trainer and inform them of the delay Raise change request for change to budget or schedule. Pull down contingency. | agree on a plan on how to proceed with trainer.
5 | Unplanned work that must be accommodated | Low | Medium | Medium | Project Sponsor | Read and understand full scope of work and communicate with the trainer before and during project to avoid delays. | Escalate to the trainer with plan of action, including impact on time and quality. | come up with an altered schedule and feedback to trainer
9 | Added workload or time requirements because of new direction, policy, or statute | Low | Medium | Medium | Project Sponsor | No ability to reduce likelihood. | Consider insurance and use Project Board to get advance notice if possible. | Project Board reviewing insurance options.
10 | Inadequate Junit testing leads to a programme that doesn't execute well | Low | Medium | High | developer | Ensure test cases/quality checks are done correctly | Raise risk immediately and raise issue if it is clear that testing inadequate or not working | solve issues by seeking help needed
11 | Make sure the database is deploying correctly | Low | Medium | High | developer | Ensure end user tests have been carried out to make sure application and database are deploying asd expected | Make a plan to test the deployment | retest to see if application and database are working
12 | Application and database security | Medium | High | High | developer | Ensure databases and application are secure and mitigate potential for hacking as much as possible. limiting the power of user accounts may give a hacker a harder time in taking complete control of the database. Protect against SQL-injection threats are to protect web-facing databases with firewalls and to test input variables for SQL injection during development. | speak with trainer and try to put measures in places to prevent future attacks | update trainer on the implementations
13 | Acts of God for example, extreme weather, leads to loss of resources, materials, premises etc. | Low | High | High | Project Manager | Ensure insurance in place. Familiarise team with emergency procedures. Where cost effective put back up systems in place e.g. generators. | Notify appropriate authorities. Follow health and safety procedures. Notify stakeholders and Project Board.
QA Academy
QA Consulting

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High